## Capacity-Early Funding spent
Capacity/Early funding activities which have already happened
Activity | Category | Description | Cost (PiP capacity funding only)
Pride in Place board member lanyards with name tags | Community outreach and engagement | Lanyards with Canvey Island Pride in Place logo that will be worn by board members during engagement events within the community | 125
1 year contract to engage a PR Marketing company (Beau Brummell Productions) | Consultancy | Required to facilitate and manage PR relations for the Board | 12000
Town Centre engagement event | Community outreach and engagement | Provide funding for visuals, artwork and other materials to be used at the engagement event | 9999
22124

## Capacity-Early Funding forecast
Capacity/Early funding activities which are planned in the next 6 months
Activity | Category | Description | Cost (PiP capacity funding only)
Active Wellbeing Suite & Partnership Hub launch event | Community outreach and engagement | Funding to provide materials for the launch event | 9999
CPBC Management costs | Management costs | Support from CPBC management fee- finance, accountancy and procruement, goverance, meeting arrangements and communication | 30000
39999

## Projects Delivered
Projects Delivered
| Target Groups | [8 empty] | Secondary Interventions (if any)
Project name | Whole community | Children & young people | Local businesses | Older residents | Ethnic minority communities | Disabled residents | VCSEs | Description | Primary intervention | Regeneration, high streets & heritage | Housing | Work, productivity & skills | Cohesion | Health & wellbeing | Transport | Saftey & security | Community Power | Education & opportunity | Organisation Type | Organisation Name | Total Capital Spend (of whole project) | Total Revenue Spend (of whole project) | Capital Spend from PiP | Revenue Spend from PiP | Additional Funding Sources | Start Date | End Date | Project Status? | Management Costs Used from Programme Funding? | Details of Management Costs (only if applicable)

## Planned Projects
Planned Projects
| Target Groups | [8 empty] | Secondary Interventions (if any) | [7 empty] | Delivery Organisation
Project name | Whole community | Children & young people | Local businesses | Older residents | Ethnic minority communities | Disabled residents | VCSEs | Description | Primary intervention | Regeneration, high streets & heritage | Housing | Work, productivity & skills | Cohesion | Health & wellbeing | Transport | Saftey & security | Education & opportunity | Organisation Type | Organisation Name | Total Capital Spend (£) | Total Revenue Spend (£) | Capital Spend from PiP (£) | Revenue Spend from PiP (£) | Additional Funding Sources | Planned Start Date | Estimated End Date | Project Status? | Management Costs Used from Programme Funding? | Details of Management Costs (only if applicable)
Canvey Lake Regeneration | Yes | [6 empty] | Regeneration of Canvey Lake is project 7 of the regeneration plan. Project 7 reflects public desire for Canvey Lake and its surrounds to be a usable space for the community with a particular emphasis on family use. In order to facilitate the evolution of this open space and encourage more uses and investment, the water quality issue must be addressed first, coupled with improved information for the public and users. The lake and park is a critical part of the Regeneration Plan’s Desire Lines project, that connects areas of the town together through enhanced and more accessible open spaces. | Regeneration, high streets and heritage |  |  |  | Yes |  |  |  |  | Local authority | Castle Point Borough Council | 1000000 | 0 | 500000 | 0 | Local authority | 2027-01-04 | 2027-03-31 | Planned | No
Canvey Lake education program | Yes | [6 empty] | Residents are very interested in water quality matters related to the Lake, and also in the activity that is now underway by the Council in terms of monitoring and treatments. There are significant levels of curiosity around what can be, and is being done in relation to water quality and wildlife. It is suggested that ongoing improvement works should be supported by a community education and engagement programme. There is an opportunity for this programme not only to engage with local residents and visitors to the Lake, but also local children and young people. There are two schools backing onto the Lake, and a further five schools, including both secondary schools within a ten minute walk of Canvey Lake Park. This therefore provides the opportunity for outdoor education and field science without having to leave the Island, broadening opportunities to gain practical skills and experience locally. | Education and opportunity |  |  |  | Yes |  |  |  |  | Local authority | Castle Point Borough Council | 0 | 25000 | 0 | 25000 | N/A | 2026-09-01 | 2027-03-31 | Planned | No
Essex Pedal Power- Canvey Island |  | Yes | [5 empty] | Pedal Power provides children and families with either free bikes or scooters, based on need to support active travel, increased physical activity, greater social connectivity, independence for young people to cycle to school and support of whole families to improve family connections. This proves to be an extremely successful scheme and also offers safety and skills training, bike construction, maintenance and repairs. Aims from this funding are: - Scale up and build on current Pedal Power infrastructure and utilise the existing model - Support a further 10 families with bikes/scooters - Support a further 20 children and young people with bikes/scooters - Support 20 NEETs with bikes – linked to active travel and local skills/employability opportunities - Provide safety and skills training - Provide bike building, maintenance and delivery support | Health and wellbeing | [5 empty] | Yes | Yes | Yes | Public sector | Castle Point and Rochford School Sport Partnership | 0 | 92000 | 0 | 38000 | UK government funding | 2026-09-01 | 2027-03-31 | Ongoing | No
Canvey Pride In Place Children and Young People Board |  | Yes | [5 empty] | Funding is being used to enable the Castle Point and Rochford School Sports Partnership to provide capacity to work with the young people in a sustained and meaningful way to ensure the views, opinions and actions of children and young people continue to lead the work of the Board. | Education and opportunity |  |  |  | Yes |  |  |  |  | Public sector | Castle Point and Rochford School Sport Partnership | 0 | 15000 | 0 | 15000 | N/A | 2026-09-01 | 2027-03-31 | Ongoing | No
Canvey Move With Us Leaders Academy |  | Yes | [5 empty] | The scheme is delivered to secondary aged students of 13 years and above over a 6 week training programme with a focus on employability/life skills such as communication, organisation, teamwork and resilience, using sport and activity as the vehicle. On completion of the 6 week course, young people are then encouraged/helped to volunteer within school and the wider community and work towards rewards. The funding will facilitate the Castle Point and Rochford School Sports Partnership to continue to develop and deliever the leadership course for an additional 48 students a year (NEETS) | Education and opportunity |  |  |  | Yes | Yes |  |  |  | Public sector | Castle Point and Rochford School Sport Partnership | 0 | 6000 | 0 | 6000 | N/A | 2026-09-07 | 2027-03-31 | Ongoing | No
Canvey Top Up Swimming ( Get Canvey Swimming) Programme |  | Yes |  |  | Yes |  |  | The funding will allow Castle Point and Rochford School Sports Partnership to work with CPBC leisure team to deliver a comprehensive programme supporting children in years 4-6 not able to swim 25m with intensive lessons over holiday periods. This funding is required as currently children able to swim 25m in Castle Point sits at 62% compared with Essex average of 76%. | Education and opportunity |  |  |  |  | Yes |  |  |  | Public sector | Castle Point and Rochford School Sport Partnership | 0 | 5000 | 0 | 5000 | N/A | 2027-02-15 | 2027-03-31 | Planned | No
King George V Pavillion - Cultural space | Yes | [6 empty] | This will be the first step in delivering the Creative Industry and Community Arts commitments as set out in the Pride in Place regeneration plan, which are to deliver: •New cultural hub in the town centre •Artist studios, performance and exhibition spaces •Public art and cultural programming •Arts Council England investment target of £3m+ •Recognition of the creative sector as a priority growth industry •Community-led cultural events and music programming •Expansion of creative engagement programmes •Strategic alignment and partnerships Also the start of Regeneration of the King George V Pavilion (KGV) is included in the regeneration plan, to enhance it as a youth and community facility to support greater participation, wellbeing and community engagement. | Regeneration, high streets and heritage |  |  | Yes | Yes | Yes |  |  | Yes | VCSE | Estuary Festival CIC | 0 | 39000 | 0 | 39000 | N/A | 2026-09-28 | 2028-03-31 | Ongoing | No
Active Wellbeing Suite & Partnership Hub | Yes |  |  | Yes |  | Yes |  | Funding paid towards development of the health and wellbeing hub within the Paddocks | Health and wellbeing | [7 empty] | Yes | Local authority | Castle Point Borough Council | 1033000 | 0 | 300000 | 0 | UK government funding | 2026-12-01 | 2028-03-01 | Planned | No
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was there some Sport England money that was matched against this?

## Neighbourhood Board Details
Neighbourhood Board Details
Answer:
Has anyone left or joined the board in the last 6 months? |  |  | Yes
If yes...
Change Type | Name | Occupation | Reason for Change | Date of Change | Notes/Comments
Leave | Joel Friedman | Chair of Canvey Jewish Trust | Time commitments did not allow Joel to attend the board meetings | 2026-06-26
Join | Jennifer Speller | Associate Director of Neighborhood Health (NHS) | Replaced previous NHS member on the board | 2026-05-22 | Replaced Caroline McCarron
Leave | Cllr Lee Scott | County Councillor | No longer Portfolio holder following local election | 2026-05-22
Join | Cllr Kevin Bell | County Councillor | New portfolio holder following local election | 2026-09-11 | Replaced Cllr Lee Scott

## Data - DO NOT USE
Regeneration, high streets, heritage
Cohesion
Housing
Work, productivity and skills
Cohesion
Community Power
Health and Wellbeing
Transport
Safety and Security
Education and opportunity

## Sheet1 (hidden)
Training | Yes
Management costs | ✓
Consultancy
Community outreach and engagement | New or improved retail, hospitality, industrial and office spaces
Other | Digital infrastructure upgrades for commercial and residential areas
Permanent full time equivalent (FTE) jobs created or safegauarded
Green retrofits to residential, public and commercial buildings
Whole community | New or improved training, educational and childcare, facilities
Children and Young People | New or improved cultural, community and sports spaces
Local Businesses | New or improved public realm
Older Residents | Improved exisiting residential units
Ethnic Minority Communities | New or improved healthcare space
Disabled Residents | New or improved public transport
VCSE
Regeneration, high streets and heritage
Housing
Work, productivity and skills
Cohesion
Health and wellbeing
Transport
Safety and Security
Education and opportunity
Private sector
VCSE
Local authority
Neighbourhood Board
Housing association
Public sector
Statuatory agency
other
N/A
Local authority
Business investment
Devolved administration
UK government funding
Other grant funding
Philanthropy
Other
Training
Management costs
Consultancy
Community outreach and engagement
Other